# Value Creation Plan v3 — Cascade Care Group

The bridge from entry (~$14M EBITDA, ~$130M EV) to exit (~$24M EBITDA, ~$220M target EV). As of Q2-26 the plan is off-track: EBITDA has eroded to ~$11M. Each workstream has an owner, target, status (RYG), the EV at stake, and the 3–6 month indicators of success. The agent ties Estimated EV Impact, What Drove EV Erosion, and Tracking on VCP back here.

## Value bridge (entry → target)

| Lever | Entry | Current (Q2-26) | Target (exit) | EV at stake | Status |
| --- | --- | --- | --- | --- | --- |
| Clinic count (de novo) | 48 | 52 | 80 | ~$45M | 🔴 stalled |
| Net collection rate | 94% | 92% | 98% | ~$25M | 🔴 worse |
| Clinician attrition | 24% | 28% | 15% | ~$20M | 🔴 worse |
| Payor mix / rate uplift | base | flat | +300bps | ~$18M | 🔴 stalled (no CFO) |
| MSO / central back-office | none | live | full | ~$22M | 🟢 on track |
| EBITDA | $14M | $11M | $24M | — | 🔴 eroding |

## Workstream 1 — De-novo clinic expansion  ·  Owner: CEO (Connolly)  ·  🔴

- Target: 48 → 80 clinics. Current: 52 (opened 4 this year vs. a plan of 12; two are underwater).

- What's driving the gap (EV erosion): No disciplined site-selection or ramp playbook; openings are opportunistic. Modeled EV drag ~$15M vs. plan.

- 3–6 month indicators of success: (1) a real de-novo playbook + pipeline; (2) the two underwater clinics to breakeven or closed; (3) ≥ 4 disciplined openings booked for H2.

- Risk: Owned by the CEO whose growth discipline is the core leadership concern.

## Workstream 2 — RCM / collections  ·  Owner: VP RCM (Park)  ·  🔴

- Target: net collection 94% → 98%; denials down.

- Current: 92% and denials up — moving the wrong way. ~$6M annualized cash drag.

- 3–6 month indicators of success: (1) net collections ≥ 95%; (2) denial rate down 200bps; (3) payor-specific denial playbooks live.

- Risk: Function out-scaled by multi-payor complexity; perf plan recommended.

## Workstream 3 — Clinician retention  ·  Owner: VP People (Frost) + CMO (Okonkwo)  ·  🔴

- Target: attrition 24% → 15%. Current: 28% — worse. Driving locum/agency costs up ~$4M.

- 3–6 month indicators of success: (1) attrition < 22%; (2) a funded retention + comp plan; (3) clinician NPS up.

- Risk: Function under-resourced (2 FTE); no CFO to approve the retention budget.

## Workstream 4 — Payor mix / rate improvement  ·  Owner: CFO (VACANT)  ·  🔴

- Target: +300bps blended rate via payor-mix shift and contract renegotiation.

- Current: stalled — no permanent CFO to own payor analytics and contracting.

- What's driving the gap (EV erosion): The open CFO seat. ~$18M of bridge value depends on this workstream and it has no owner. Modeled EV slippage ~$8M of timing/forgone uplift.

- 3–6 month indicators of success: (1) CFO hired; (2) payor analytics stood up; (3) two contracts renegotiated.

## Workstream 5 — MSO / central back-office  ·  Owner: COO (Delgado)  ·  🟢

- Target: central scheduling, credentialing, billing, and HR shared services.

- Current: live and on track — the one green workstream, built and run by the COO.

- 3–6 month indicators of success: (1) all 52 clinics on central scheduling; (2) back-office cost-per-clinic down 10%.

## Workstream 6 — EBITDA bridge  ·  Owner: CFO (VACANT) / interim  ·  🔴

- Target: $14M → $24M. Current: $11M — eroded. Mix of stalled growth, weak collections, and locum costs.

## EV-at-risk summary (people-linked)

| Risk | Linked leader | EV exposure | Note |
| --- | --- | --- | --- |
| Stalled de-novo growth | CEO (Connolly) | ~$15M drag | Core leadership concern. |
| CFO vacancy / payor uplift stalled | CFO (vacant) | ~$8M + ~$18M unowned | The escalation item. |
| Collections / denials behind | VP RCM (Park) | ~$6M cash | Perf plan recommended. |
| Clinician attrition | VP People + CMO | ~$4M locum | Under-resourced; no funding. |
| COO retention (upside protection) | COO (Delgado) | recovery hinges here | Promote/retain — the catastrophic loss to avoid. |

## Headline

Off-plan and escalating. EBITDA has eroded from $14M to $11M. The recoverable path is: promote/retain the COO, close the CFO hire, put RCM on a plan, and fund clinician retention. Five of six workstreams are red; the one green (MSO) is the COO's.